## Dvpt. & Release STAGES
Revised: |  | 2019-06-14
Stage | Vers. | Description | Core Aspects | Status
0 | 0 | Wireframe | Representative layout of BuilderDC windows (Excel) | Done
0 | 0 | Mockup | BuilderDC implemented in XAML/WPF with static dummy data, no database connectivity | Done
1 | 0.1 | Prototype with login | Start of Prototype, support for log in process, connectivity to the underlying MDB database files, display of hierarchy. | In Progress
2 | 0.2 | Prototype with facility edit | Ability to add Building comments & attach photo files (like BRED)
3 | 0.3 | Prototype with inventory functionality | Ability to add systems, components, sections and edit inventory
4 | 0.3.5 | Prototype with inspection functionality | Ability to add/edit inspections & attach photos (like BRED)
5 | 0.4 | Photo Mgmt & Barcodes | Integrated Photo taking & management, Barcode reading & resolution of issues.
6 | 0.5 | Functional replacement 'FR' | Can be used as a straight replacement of BRED V3.5 for our typical DCR inspections (with only minor differences) No QC Tab functionality No Copy functionality
7 | 0.6 | FR plus Copy support | Copy functionality integrated & resolution of issues.
8 | 0.7 | FR plus QC - Inventory | QC tab for Inventory functional (i.e. perform all Business Rule checks that BQC does that are inventory-related) & resolution of issues.
9 | 0.8 | FR plus QC - Inspections | QC tab for Inspections functional (i.e. perform all Business Rule checks that BQC does that are inspection-related) & resolution of issues.
10 | 0.9 | Changes based on User feedback | Incorporate most significant changes/enhancements based on feedback of BQC QC & Data Managers & Beta users. User documentation.
11 | 1 | Full Release | Inspectors switch over from BuilderRED to BuilderDC, a team at a time.

## General SOW ~ Stage 1 - 6
Specification for BuilderDC 'BDC' V1 prototype, phase 1
Note: Specifically adapted from full spec for the needs of prototype developer
Revised: May 31, 2019
General objectives
Establish functional equivalence with BuilderRED 'BRED' V3.5 with specific platform differences, deliberate omissions, and a set of changes and additions as detailed here
Platform differences
BRED is a Winforms VB.NET-based project; BQC is C# / WPF / XAML-based Visual Studio 2017 solution
The .NET framework for BQC shall be V4.7.2 and optionally 3.5 SP1 if needed (i.e. Windows 10, and as used by VS 2017)
BRED uses Infragistics and Teleric third-party components; BQC does not, instead uses controls native to WPF.
BRED's Help file is CHM; BQC uses PDF files (more convenient to maintain by non-technical writers)
Deliberate Omissions of BRED functionality ~ What does NOT get implemented in BuilderDC V1
Functionality Mode
Add Building & Delete Building
View Menu (Inspection <-> Inventory Mode on toolbar / Auto refresh of trees / No user control over measurement system)
Tools Menu
New Copy Sections functionality (as well as inventory) in BuiderDC
Option for Open Last File on startup is replaced by by auto selection on new Log in screen
Reports will be replaced by new ones as needed by inspectors
Save & Cancel buttons on main toolbar: Unlike BRED, BuilderDC auto saves changes unless the CANCEL button is selected
Comments and Images buttons on main toolbar: BDC shows these automatically and offer Add/Edit buttons for these on the various Uis instead
Inspection Summary ( will be replaced by QC - Inspection Tab that focuses on issues)
Work Items (not used for BUILDER FCA projects that Cardno GS is engaged in)
Inspection UI ~ Type = Distress (We only support DCRs)
Inspection UI ~ Type = PM Inspection (We only support DCRs)
Inspection UI ~ Method = Sampling (We only support 'Not Sampling')
Also not to be shown, unsupported:
Samp. Qty, Location , % Insp.
Checkbox: Non-representative
Inventory UI ~ Functional Area
CHANGES of functionality ~ General Functional Equivalency: V0.1 -> V0.5
LOG IN Process
User needs to select the designated BUILDER project's Poject Configuration file in addition to inspector's BRED file
User is presented with project-specific list of users at same time of BRED file selection
General Changes
Folder & File Locations: Refer to separate spreadsheet: BDC_Locations of Files,Settings&DBsUsed.xlsx
Help file: Use a placeholder PDF file called BuilderDC_UsersGuide.pdf
Instead of using BRED.mdb as the operational DB, use BuilderDC.mdb
Additions, over & beyond BRED
Implement Barcode reader, using a stable & supported Open Source of Zxing.net (if possible)
GitHub folder
Reading of Project Config MDB (Limited)
List of BDC users for the project
qry_BDC_ActiveUsers (filters on IsActive is 1 and Disabled = 0)
Required photo resolution: BDC_Config_Project.PhotoResolutionDefault
Photonaming parameters
Photo handling functions ~ For details see ImageManifest.csv_Spec.xlsx
Automatic naming per BDC project config values
Auto resizing per BDC project config values (typically 800 x 600)
Ability to rotate left & right by 90 degrees
Ability to control usage of flash: Off or Auto (to preserve battery power)
On-the-fly addition/changes to Bredpackage (= zip file of image manifest for the BRED file)