## Sheet1
ID | Area | Task | Status
A1 | App | Add left justified Label style
Add center justified Label style
Add right justified Label style
Add bold Label stytle
Add gray BG black bounded Label style
L1 | Login | Create View and ViewModel | Done
L2 |  | Blue border and gray BG
L3 |  | Add Build Config caption
L4 |  | Add Build Config TextBox and bind to VM
L5 |  | Save/Retrieve Build Config contents to user resources
L6 |  | Add Build Config Select button
L7 |  | Bind Build Config Select button Command to VM
L8 |  | Add BRED caption
L9 |  | Add BRED TextBox
L10 |  | Add BRED Select button
L11 |  | Bind BRED Select button Command to VM
L12 |  | Add Browse dlg to Select Command using saved path
L13 |  | Save/Retrieve last folder to user resources
L14 |  | Add Inspector caption
L15 |  | Add inspector ComboBox
L16 |  | Bind ComboBox Source to VM
L17 |  | VM inspector source populated from config file
L18 |  | ComboBox disabled until source list populated
L19 |  | Add MORE button
L20 |  | Disable MORE until config file read
L21 |  | Bind MORE Command to VM
L22 |  | Add LOGIN button
L23 |  | Disable LOGIN until Config, BRED and Inspector specified
L24 |  | Bind LOGIN Command to VM
L25 |  | LOGIN command closes Login view and displays ShellView
S1 | Shell | Create ShellView and ShellViewModel | Done
S2 |  | Bind Title to VM
S3 |  | Title string constructed from Build DC + pathname of a file
S3.Q1 |  | G: What file?
S4 |  | Add Menu
S5 |  | Add Submenus
S6 |  | Add Toolbar
S7 |  | Add buttons to Toolbar
S8 |  | Add TreeView
S9 |  | Bind TreeView source to ShellViewModel
S10 |  | Details TreeView to all expanded
S11 |  | Bind selected TreeView item to VM
S12 |  | Add grid splitter
S13 |  | Add TabView
S14 |  | Add Status Bar
S15 |  | Add Status Bar contents and bind to ShellViewModel
B1 | Bluebeam | G: What is this? Need direction on this. | Ask G
F1 | Facility | Add Facility View and ViewModel
Add 'Identity' items
Add 'Faility Comment' TextBox
Add 'Photos thumbnails' Listbox
Add 'Address' items
Add 'Point of contact' items
I1 | Inventory | Add Inventory View and ViewModel
IS1 | I-Section | Add InventorySection View and ViewModel
IS2 |  | Add Section Name list control
IS3 |  | Add Section ComboBox
IS4 |  | Add Equipment Category caption and bind to VM which changes
IS4.Q1 |  | G: What are the rules for Category caption change? | Ask G
IS5 |  | Add Category ComboBox
IS6 |  | Add Component Type Label and ComboBox
IS7 |  | Add Quantity
IS8 |  | Add year Installed
IS9 |  | Add Functional Area
IS10 |  | Add Not Energy
IS11 |  | Add Painted
IS12 |  | Add Section Comment
IS13 |  | Add Remember
IS14 |  | Add Photos
IS15 |  | Add Photos List
IS16 |  | Add current inspector date
IS17 |  | Add Cancel button
IS18 |  | Add Delete Section button
IS19 |  | Add 'Add Section' button