## Sheet1
ID | Area | Task | Status | Date
A1 | App | Add left justified Label style
A2 |  | Add center justified Label style
A3 |  | Add right justified Label style
A4 |  | Add bold Label stytle
A5 |  | Add gray BG black bounded Label style
A6.Q1 |  | Can they provide an example Access database for development?
A7.Q1 |  | Are pictures stored as Access data or as local files?
A8.Q1 |  | Will the database be server based?
L1 | Login | Create View and ViewModel | Done
L1.Q1 |  | Should we serialize the information for context restore? Rlh - I was thinking of just shoving it into user setting strings. | Done
L1.Q1.1 |  | Add application user strings to contain last configuration and BRED file. Save on Log In click. Restore when Log In displays. See L5. | Done
L2 |  | Blue border and gray BG | Done
L3 |  | Add Build Config caption | Done
L4 |  | Add Build Config TextBox and bind to VM | Done
L5 |  | Save/Retrieve Build Config contents to user sesttings string resources | Done
L5.Q1 |  | Is the configuration content stored in a file? | xxx
L5.Q1.1 |  | no. Save to user setting string. | xxx
L6 |  | Add Build Config Select button | Done
L7 |  | Bind Build Config Select button Command to VM | Done
L8 |  | Add BRED caption | Done
L9 |  | Add BRED TextBox | Done
L10 |  | Add BRED Select button | Done
L11 |  | Bind BRED Select button Command to VM | Done
L12 |  | Add Browse dlg to Select Command using saved path
L12.Q1 |  | Need to save/retrieve path
L12.Q1.1 |  | See L5. Save to user setting string.
L13 |  | Save/Retrieve last folder to user resources | Done
L14 |  | Add Inspector caption | Done
L15 |  | Add inspector ComboBox | Done
L16 |  | Bind ComboBox Source to VM | Done
L17 |  | VM inspector source populated from config file | Done
L17.Q1 |  | Is this file based or will we be connecting to a server? | N/A
L18 |  | ComboBox disabled until source list populated
L19 |  | Add MORE button | Done
L20 |  | Disable MORE until config file read | Done
L21 |  | Bind MORE Command to VM | Done
L21.Q1 |  | What does "More" do? | Ask G.
L22 |  | Add LOGIN button | Done
L23 |  | Disable LOGIN until Config, BRED and Inspector specified | Done
L24 |  | Bind LOGIN Command to VM | Done
L25 |  | LOGIN command closes Login view and displays ShellView | Done
L26 |  | Add Cancel button to terminate application | Done
L27.FB |  | G: 1st line: Builder needs to be all cap: BUILDER Data Collecto | Done | 2019-03-30
L28.FB |  | G: Logo edges look bad. In email I have attached 3 alternatives to try. Be sure to maintain aspect ratio. | Addressed | 2019-03-30
L28.FB.1 |  | rlh - Replaced the existing logo with a new one. New image is *much* nicer. | Done | 2019-03-30
L29.FB |  | G: • Can we drop all the wasted space on top and bottom, have the soft gray background and (Cardno) dark blue border | Done | 2019-03-30
L30.FB |  | G: • The icons in front of the three text boxes are too small to look good; Either get them bigger or remove. | Done | 2019-03-30
L31.FB |  | G: • The text in the text boxes is too small as well as the 'Inspector is required' message, larger font please. | Partially addressed | 2019-03-30
L31.FB.R1 |  | Increased the text box and combo box font size. However, the validation error string will be a little more difficult. It can be done, just not a trvial change. Will do this later. |  | 2019-03-30
L32.FB |  | G: o To note: It is possible that the BRED file to use line can get long; That text box should be auto wrap and expand to two lines of height as needed | Addressed | 2019-03-30
L32.FB.R1 |  | Changed the TextBox from to allow wrapping. When a wrap occurs then the box gets taller to accommodate the text. | Done | 2019-03-30
L33 |  | Need to get rid of main window flash prior to Login display.
S1 | Shell | Create ShellView and ShellViewModel | Done
S2 |  | Bind Title to VM | Done
S3 |  | Title string constructed from Build DC + pathname of a file | Done
S3.Q1 |  | G: What file? | xxx
S3.A1 |  | I believe this is the BRED file selected on the Login page. | xxx
S3.Q2 |  | What data is stored in the BRED file?
S3.Q3 |  | What data is stored in the config file?
S4 |  | Add Menu | Done
S5 |  | Add Submenus | Done
S6 |  | Add Toolbar | Done
S7 |  | Add buttons to Toolbar | Done
S8 |  | Add TreeView | Done
S9 |  | Bind TreeView source to ShellViewModel | Done
S10 |  | Details TreeView to all expanded | Done
S10.Q1 |  | Need better definition of tree items / filters.
S11 |  | Bind selected TreeView item to VM | Done
S12 |  | Add grid splitter | Done
S12.Q1 |  | Is this done? What else is required? | xxx
S13 |  | Add TabView | Done
S14 |  | Add Status Bar | Done
S15 |  | Add Status Bar contents and bind to ShellViewModel | Done
S15.Q1 |  | Should the staus bar remain on the viewable page and the scroll only affect the interior (e.g. Inventory details)? | Closed
S15.Q1.1 |  | rlh - yes | Closed
S16.Q1 |  | Tear-off sidebar?
S17.FB |  | G: Misunderstanding. Those are sub menu items, not another toolbar. Remove from Shell. | Done | 2019-03-30
S17.FB.1 |  | Removed the spurious Toolbar and updated the remaining one. | Done | 2019-03-30
S18.FB |  | G: Make title bar font bigger by approx 20% | Pending | 2019-03-30
S18.FB.1 |  | This is possible but not trivial. Will delay implementation until after more functional things have been completed. | In process
S19.FB |  | G: Make menu text bigger | Done | 2019-03-30
S20.FB |  | G: Make toolbar taller with more space between menu and below. | Done | 2019-03-30
S21.FB |  | G: Build (aka Inventory) and Inspection icons should both be present with some means of indicating what mode currently in, Inventory or Inspect. | Pending
S21.FB.1 |  | Added the toolbar buttons but 'currently selected' indication is not yet implemented | In process | 2019-03-30
S22.FB |  | G: Add system and Delete system icons. As we need to distinguish adding system from adding component from adding Section, I have created three simplistic placeholder PNG files to use as toolbar images. Same thing for delete.
S22.FB.1 |  | The 'add system and delete system icon' thing is a little confusing. Can you elaborate on that? | In process | 2019-03-30
S23 |  | Modify the Tab item style to be fat finger compatible and more colorful on selection.
S24 |  | Remember and reassert window placement between sessions | Done | 2019-03-31
S25 |  | Bug: Before Login shows, the Shell briefly flashes. It should not. | Done | 2019-03-31
G1.FB | General | G: • Text boxes in general: Too much space above and below the text, uses up a lot of valuable vertical space.
B1 | Bluebeam | G: What is this? Need direction on this. | Ask G | 2019-03-31
F1 | Facility | Add Facility View and ViewModel | Done
F2 |  | Add 'Identity' items | Done
F3 |  | Add 'Faility Comment' TextBox | Done
F4 |  | Add 'Photos thumbnails' Listbox | Done
F4.Q1 |  | Picture carousel?
F5 |  | Add 'Address' items | Done
F6 |  | Add 'Point of contact' items | Done
F7.FB |  | G: Need more space between Alt ID and Facility comment section
F8.FB |  | G: Need more space between Facility comment and Photo carousel.
F9.FB |  | G: • The text box for Quantity is too small: should accommodate 888,888.88 You can adjust Building ID, Year built and Alternate ID to be the same, as shown in the wire frame.
F10.FB |  | G: • Address section: No need for 2nd address line, please remove
I1 | Inventory | Add Inventory View and ViewModel
IS1 | I-Section | Add InventorySection View and ViewModel
IS2 |  | Add Section Name list control
IS3 |  | Add Section ComboBox
IS4 |  | Add Equipment Category caption and bind to VM which changes
IS4.Q1 |  | G: What are the rules for Category caption change? | Ask G
IS5 |  | Add Category ComboBox
IS6 |  | Add Component Type Label and ComboBox
IS7 |  | Add Quantity
IS8 |  | Add year Installed
IS9 |  | Add Functional Area
IS10 |  | Add Not Energy
IS11 |  | Add Painted
IS12 |  | Add Section Comment
IS13 |  | Add Remember
IS14 |  | Add Photos
IS15 |  | Add Photos List
IS16 |  | Add current inspector date
IS17 |  | Add Cancel button
IS18 |  | Add Delete Section button
IS19 |  | Add 'Add Section' button
IS20.FB |  | G: • Supplied you with Add Component and Add Section icons to replace the (identical) placeholders you have used. | Done | 2019-03-31
IS21.FB |  | G: • I will work on place holder icons for Copy Section and Copy Inventory.
IS22.FB |  | G: • Section Name, Equip Cat and Component Type only need a single line - rlh: From the notes it looks like these values cannot be directory edited by the user. Instead, the user selects a member for a list of possibilities. Accordingly, DropDown ComboBox's are being used for these items, not Labels or TextBoxes. | Possible misunderstanding. Need to ask G. Waiting for response | 2019-03-31
IS23.FB |  | G: • The value for DCR Rating are, in order from top to bottom: G+, G G-, Y+, Y, Y-, R+, R, R- (nine possible ratings. Same for P/C ratings.
IS24.FB |  | G: Make photo carousel taller in all Views.
Toolbar
T1 |  | Add buttons that show and hide depending upon the currently active tab control | Done | 2019-03-30
T2 |  | Ask G for an image for Copy Inventory button | Pending | 2019-03-31
T3 |  | Ask G for an image for Copy Inspection button | Pending | 2019-03-13
T4 |  | Ask G for an image for Copy Sections button | Pending | 2019-03-13
| CM | Comment Popup
CM1 |  | Add View and ViewModel class skeletons | Done | 2019-03-31
CM2 |  | Add toolbar and connect images to each button | Done | 2019-03-31
CM3 |  | Get more info on what data and controls are in the View from G.
CM4 |  | Ask G to clarify, what launches the Comment Popup? | Pending
CM5 |  | Connect Shell buttons to show the View
| CI | Comment on Inspection
CI1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
CI2 |  | Add toolbar and connect images to each button | Done | 2019-03-31
CI3 |  | Add radio buttons
CI4 |  | Create a style for radio buttons so that they match the spec
CI5 |  | Connect Inspection's 'Inspection Comment' button to launch popup.
| CC | Copy Comment
CC1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
CC2 |  | Add Source row
CC3 |  | Add Related to current row
CC4 |  | Add Rated as row
CC5 |  | Add Search term row
CC6 |  | Add Facility code DCR Comment data grid
CC7 |  | Add bottom button row
CC8 |  | Connect Shell buttons to show the View
| CN | Copy Inventory
CN1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
CN2 |  | Add Source Facility row
CN3 |  | Add Target Facility row
CN4 |  | Add Section Name row
CN5 |  | Add Systems to copy rows
CN6 |  | Add Options cluster
CN7 |  | Add bottom button row
CN8 |  | Connect Shell buttons to show the View
| PM | Photo Managerment
PM1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
PM2 |  | Add Pending cluster
PM3 |  | Add Existing cluster
PM4 |  | Add Details cluster
PM5 |  | Add Title and Description data collection elements
PM6 |  | Connect Shell buttons to show the View
| CP | Camera UI/Capture Photo
CP1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
CP2 |  | Add toolbar and buttons | Done | 2019-03-31
CP3 |  | Add Image area | Done | 2019-03-31
CP4 |  | Connect Cancel and OK buttons
CP5 |  | Customize toolbar button appearance
CP6 |  | Connect Shell buttons to show the View
| AS | Add System
AS1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
AS2 |  | Add label, combo and buttons to View | Done | 2019-03-31
AS3 |  | Connect OK and Cancel buttons to ViewModel
AS4 |  | Connect Shell buttons to show the View
| AC | Add New Component
AC1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
AC2 |  | Add label, combo and buttons to View | Done | 2019-03-31
AC3 |  | Connect OK and Cancel buttons to ViewModel
AC4 |  | Connect Shell buttons to show the View