## Sheet1
ID | Area | Task | Status | Last Activity | Notes
| General | This section is concerned with tasks that relate to general
| GC | General Questions
GC.Q1 |  | Do we need to make custom "Message Box" for thoses single-line questions? It's related to that whole "fat-fingers" style. There are some Material-Design concepts we could use. Here are some examples | Closed | 2019-04-20
GC.Q1.FB.1 |  | https://github.com/denpalrius/Material-Message-Box | Closed | 2019-04-20
GC.Q1.FB.2 |  | GD: Look good, tidy, very similar to standard way of working Message boxes. | OK to implement. | 2019-04-15
GC.Q1.2 |  | Prototype Message box with large font headers implemented on Microphone OFF Tool for review. | Done | 2019-04-20
G1.FB |  | G: • Text boxes in general: Too much space above and below the text, uses up a lot of valuable vertical space.
G2 |  | DatePicker's vertical text alignment is Top. Can it be changed to Center?
| AC | Add New Component
AC1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
AC2 |  | Add label, combo and buttons to View | Done | 2019-03-31
AC2.FB1 |  | Label should read: "ADD NEW COMPONENT" (I.E. Let's standardize on ALL CAPs for Window handle bar, considering it is difficult to make a bigger font (it seems) | Done | 2019-04-17
AC3 |  | Connect OK and Cancel buttons to ViewModel | Done | 2019-04-08
AC4 |  | Connect Shell buttons to show the View | Done | 2019-04-08
| AS | Add System
AS1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
AS2 |  | Add label, combo and buttons to View | Done | 2019-03-31
AS3 |  | Connect OK and Cancel buttons to ViewModel | Done | 2019-04-08
AS4 |  | Connect Shell buttons to show the View | Done | 2019-04-08
| App | Application
A1 |  | Add left justified Label style | Done
A2 |  | Add center justified Label style | Done
A3 |  | Add right justified Label style | Done
A4 |  | Add bold Label stytle | Done
A5 |  | Add gray BG black bounded Label style | Done
Bluebeam
B1.Q |  | G: What is this? Need direction on this. | Done | 2019-03-31
B1.Q2 |  | GD: Trigger a File Open dialog. File type: XLSX, Caption: "Select Bluebeam Excel file (placeholder)" OK/Cancel buttons. Nothing is expected to happen in the mockup regardless what spreadsheet the user may/may not select. FYI only: In prototype stage, we will read data in spreadsheet and present as text in the window that you can see in the wireframe, Main tab, Cells M8- S27. | Done | 2019-04-08
B1.FB |  | GD: the file type is actually .CSV, not xlsx. | Done | 2019-04-17
| CC | Copy Comment
CC1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
CC1FB1 |  | Larger, matching fonts to other areas
CC1FB2 |  | Label My Saved Com > My saved comments | Done | 2019-04-14
CC1FB3 |  | Label ComponentFacility > Facility: | Done | 2019-04-14
CC1FB4 |  | Lab el ComponentInvents > Component Type: | Done | 2019-04-14
CC1FB5 |  | Label Yellow > Green | Done | 2019-04-14
CC1FB6 |  | data rows not selected: white Backgrouns (for contrast) | Done | 2019-04-20
CC1FB7 |  | Increase height: near double so we can show a lot more comments without user having to page. Also double width, giving the extra space to the comment column | Done | 2019-04-14
CC1FB8 |  | The comment colum will need to wrap, so user can see full comment text, expanding row height as needed, if possible. If not, set aside two rows of text per comment. | Done | 2019-04-14
CC1FB9 |  | Windows caption: SELECT COMMENT TO COPY… (is used for different types of comments) | Done | 2019-04-17
CC2 |  | Add Source row | Done | 2019-03-31
CC2FB |  | Relabel BRED to BRED file | Done | 2019-04-17
CC3 |  | Add Related to current row | Done | 2019-03-31
CC3FB1 |  | Relabel System > System Type | Done | 2019-04-17
CC4 |  | Add Rated as row | Done | 2019-03-31
CC5 |  | Add Search term row | Done | 2019-03-31
CC6 |  | Add Facility code DCR Comment data grid | Done | 2019-03-31
CC7 |  | Add bottom button row | Done | 2019-03-31
CC8 |  | Connect Shell buttons to show the View | Done | 2019-04-14
CC8.Q1 |  | Where / when is the Copy Comment supposed to be / show? | Done | 2019-04-13
CC8.Q1.A1 |  | Copy button on the Comment Popup UI. | Done | 2019-04-18
| CI | Comment on Inspection
CI1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
CI2 |  | Add toolbar and connect images to each button | Done | 2019-03-31
CI3 |  | Add radio buttons | Done | 2019-04-14
CI3.FB |  | The No Recomm. Radio button is default, please spell out: No recommendation. | Done | 2019-04-14
CI4 |  | Font size: larger to match other Uis done
CI5 |  | Connect Inspection's 'Inspection Comment' button to launch popup. | Done | 2019-04-08
C16 |  | Add Copy Comment icon / link to copy inspection comment popup | Done | 2019-04-14
| CM | Comment Popup
CM1 |  | Add View and ViewModel class skeletons | Done | 2019-03-31
CM2 |  | Add toolbar and connect images to each button | Done | 2019-03-31
CM3 |  | Get more info on what data and controls are in the View from G. | Done | 2019-04-18
CM4 |  | Ask G to clarify, what launches the Comment Popup? | Done
CM5 |  | Connect Shell buttons to show the View | Done
CM6 |  | Update the Title depending upon what comment is being updated | Done | 2019-04-14
CM7 |  | Ask G: Where does <IDENTIFIER CONTINUEED> come from? | Done
CM7FB1 |  | GD: This gray background area reinforces exactly which comment the user is working on, <CONTINUED> is a wrap-artound continuation of the first gray row. For example and structure see the WF, Cm tab, areas L4 - S8 | Done | 2019-04-15
CM8 |  | Ask G: How does Delete work? What triggers a delete of the current comment? | Done | 2019-04-14
CM8FB1 |  | GD: There is no delete here because clearing all text is a sign for BDC to set the comment to NULL | Done | 2019-04-15
CM9 |  | Ask G: What is 'auto stamping'? | Done | 2019-04-16
CM9.1 |  | Will be implemented in release version. | Done | 2019-04-17
CM9FB1 |  | GD: PT -- Identifies inspector and date/time in a standardized format. See explanation on Cm tab, cells L12 - T16 | Done | 2019-04-17
| CN | Copy Inventory
CN1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
CN1FB1 |  | Label Copy InspectionComments > Copy Inspections | Done | 2019-04-14
CN1FB2 |  | Larger font, similar to used elsewhere. | Done | 2019-04-17
CN1FB3 |  | Year text cell to be just large enough for 5 digits (the 5th being a mistake) | Done | 2019-04-14
CN1FB4 |  | Please add some padding to the left (now too easy to click to the left of checkboxes and actually take user to a different window) | Done | 2019-04-17
CN2 |  | Add Source Facility row | Done | 2019-04-17
CN2.Q1 |  | Is Source Facility a free-entry or should this be a combo-box with existing? If combo-box, should it allow new items? | Done | 2019-04-17
CN2.Q1.FB |  | Not free entry, is a short list of facilities in the BRED (typ. 1 - 10). So picklist, no additions. Example for mockup: 11507 - National Guard Readiness Center, 11612 - Facility # 2. | Done | 2019-04-17
CN3 |  | Add Target Facility row | Done | 2019-04-17
CN3.FB1 |  | Example for mockup: 11507 - National Guard Readiness Center, 11612 - Facility # 2. | Done | 2019-04-17
CN4 |  | Add Section Name row | Done | 2019-04-17
CN4.FB1 |  | Example entries in Mockup: FL1, FL2, EAST WING, WEST WING, MEZZANINE (all all caps) | Done | 2019-04-17
CN4.Q1 |  | Ask G: What does (Section = Node) mean? | Pending | 2019-04-18
CN5 |  | Add Systems to copy rows | Done | 2019-04-17
|  | Good as you have it. | Done | 2019-04-17
CN6 |  | Add Options cluster | Done | 2019-04-17
CN6.B1 |  | Year built needs to change color / enabled with "Override" checkbox | Done | 2019-04-17
CN7 |  | Add bottom button row | Done | 2019-04-17
CN8 |  | Connect Shell buttons to show the View | Done | 2019-04-17
| CP | Camera UI/Capture Photo
CP1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
CP2 |  | Add toolbar and buttons | Done | 2019-03-31
CP2FB1 |  | GD: Need fpor photo size control has been deleted from spec. Please remove those three items | Done | 2019-04-15
CP2FB2 |  | GD: For energy conservation, need to provide users control over flash usage, preference is off. These are a set, i.e. to indicate which mode is on. | Done | 2019-04-15
CP3 |  | Add Image area | Done | 2019-03-31
CP3FB1 |  | Please increase in size to show a 800 x 600 pixel photo plus surroundings of course. Note: 800 x 600 is the standard photo size in BUILDER projects, so 100% represnertative of what end users will see eventually. | Done | 2019-04-15
CP4 |  | Connect Cancel and OK buttons | Done
CP5 |  | Customize toolbar button appearance | Done
CP6 |  | Connect Shell buttons to show the View | Done
CP7 |  | Link Capture into the Photo Management | Done | 2019-04-15
Facility
F1 |  | Add Facility View and ViewModel | Done | 2019-03-29
F2 |  | Add 'Identity' items | Done | 2019-03-29
F2.FB1 |  | Change Facility ID to a number: 11507 | Done | 2019-04-18
F3 |  | Add 'Faility Comment' TextBox | Done | 2019-03-29
F4 |  | Add 'Photos thumbnails' Listbox | Done | 2019-03-29
F4.Q1 |  | Picture carousel is a hard coded script, not a true carousel. | Done | 2019-03-29
F5 |  | Add 'Address' items | Done | 2019-03-29
F5.FB1 |  | Somehow the ZIP/Postal code is being bumped to a new row. Should be on same row as State/Prov. | Done | 2019-04-18
F6 |  | Add 'Point of contact' items | Done | 2019-03-29
F7.FB |  | Need more space between Alt ID and Facility comment section | Done | 2019-03-31
F8.FB |  | Need more space between Facility comment and Photo carousel. | Done | 2019-03-31
F9.FB |  | The text box for Quantity is too small: should accommodate 888,888.88 You can adjust Building ID, Year built and Alternate ID to be the same, as shown in the wire frame. | Done | 2019-04-02
F10.FB |  | Address section: No need for 2nd address line, please remove | Done | 2019-04-01
F11.FB |  | Comment with light yellow background rather than orange please, BDC’s standard for text that can be edited but not where displayed. | Done | 2019-04-02
F12.FB |  | In this 3rd iteration, somehow cells that were light gray background are showing up as white again. | Done | 2019-04-02
F13.FB |  | Only ones that should have white background are ones the user can edit: Width, Depth and Floor Height | Done | 2019-04-02
F13.FB.1 |  | Ask G: What about Quantity? Where does its data come from? | Done | 2019-04-18 | Answer
F14 |  | Bug: Width, Depth and Floor Height should be editable but are not. | Done
F14.Q1 |  | Should "Total Area" be calculation or user input? | Done | 2019-04-18
F14.FB10 |  | GD: There is no "Total Area" on the Facility tab, I suppose you mean Quantity. That data is in the BRED file, but the user can adjust | Done | 2019-04-18
F15 |  | Photo Button: To launch the Photo Mgmt Popup, not the Camera popup. The Camera popup is lauched from the Photo Mgmt UI. | Done | 2019-04-15
Inventory
I1 |  | Add Inventory View and ViewModel | Done
I2 |  | Add Tab control | Done
I2FB1 |  | Change "Details" to "Details (1)" on the tab (The # represents the number of details) | Done | 2019-04-18
I3 |  | Add color to Tab control | Done | 2013-04-06
| I-Detail | Inventory Details
ID1 |  | Add InventoryDetails View and ViewModel | Done
ID2 |  | Add Current Section label and a read only data label | Done
ID3 |  | Add Detail Selector caption and dropdown list combobox | Done
ID4 |  | Add green BG to Current Section and Detail Selector caption labels | Done | 2019-04-07
ID5 |  | Add Detail ID and Location label and data TextBox | Done
ID6 |  | Add Model and Serial Number label and data TextBox | Done
ID7 |  | Add Manufacturer label and data ComboBox | Done
ID7.Q.1 |  | Ask G: Pick list or can user type in a value? | Done | 2019-04-18 | Combo: Select or Type in
ID8 |  | Add Capacity label and data TextBox | Done
ID9 |  | Add Equipment Type label and data TextBox | Done
ID10 |  | Add Equip. Make and ComboBox | Done
ID10.Q.1 |  | Ask G: Pick list or can user type in a value? | Done | 2019-04-18 | Combo: Select or Type in
ID11 |  | Add Date Manufactured label and DatePicker | Done
ID12 |  | Add Year Installed and data TextBox | Done
ID13 |  | Add Control Type/Make label and data TextBox | Done
ID14 |  | Add Warranty Date label and DatePicker | Done
ID15 |  | Add Warranty Company and data TextBox | Done
ID16 |  | Add Warranty Date 2 label and DatePicker | Done
ID17 |  | Add Warranty Company 2 label and data TextBox | Done
ID18 |  | Add Detail Command image, blue background label and Comment field which is edited elsewhere | Done
ID19 |  | Add mocked Detail Photos image carousel | Done
ID20 |  | Add Cancel Edit, Delete Detail, Add Detail and Copy Detail image buttons | Done
ID20.FB |  | Relocate ID20's buttons so that all are on the same row | Done | 2019-04-03
ID21.FB |  | Detail Comment should be soft yellow, not gray | Done | 2019-04-02
ID22.FB |  | G: Green arrow next to Detail Selector is missing. Add it. | Done | 2019-04-03
ID23.FB |  | G: The barcode image is actually a command button | Done | 2019-04-07
ID23.FB.2 |  | Ask G: what does the barcode button do? | Done
ID23.FB.3 |  | Ask G: Barcode button launches a barcode reader. Where is this reader? | Done |  | PT Answer
ID24 |  | Ask G: What is the (#)? | Done |  | PT Answer
ID25 |  | Curent Section and Detail Selector cells are supposed to have a green background. | Done | 2019-04-04
ID26 |  | Add green down button to Current Selector. | Done | 2019-04-07
ID27 |  | Click on green down button increments through the list in the associated combo. | Done | 2019-04-07
ID28 |  | Bug: Warr. Company 2: doesn't have a 2. | Done | 2019-04-07
ID29 |  | Detail Comment button should bring up Add/Edit/Delete comment box when clicked. | Done | 2019-04-06
ID30 |  | Comment should be Read Only. | Done | 2019-04-07
ID31 |  | Click on Detail Photos button should bring up photo adder/editor box. | Done | 2019-04-06
ID31FB1 |  | Photo Button: To launch the Photo Mgmt Popup, not the Camera popup. The Camera popup is lauched from the Photo Mgmt UI. | Done | 2019-04-14
ID32 |  | Make bottom buttons look like wireframe's. | Done | 2019-04-07
ID33 |  | Ask G: How should a click on 'Cancel Edit' work? | Done | 2019-04-18 | Answer
ID34 |  | Ask G: How should a click on 'Delete Detail' work? | Done | 2019-04-18
ID34FB1 |  | present dialog: "Are you sure you want to delete current section and related info?" OK / Cancel. (real action beyond that is for PT) | Done | 2019-04-18
ID35 |  | Ask G: How should Add Detail work? | Pending | 2019-04-18
ID36 |  | Ask G: How should Copy Detail work? | Pending | 2019-04-18
| I-Section | Inventory Section
IS1 |  | Add InventorySection View and ViewModel | Done
IS2 |  | Add Section Name list control | Done
IS3 |  | Add Section ComboBox | Done
IS4 |  | Add Equipment Category caption and bind to VM which changes | Done
IS4.Q1 |  | G: What are the rules for Category caption change? | Done | 2019-04-18 | Answer
IS4.Q1.1 |  | GD: If current selected node in treeview has System starting with D or E then 'Equiment Category', all others 'Material Category'. | Pending | 2019-04-18
IS5 |  | Add Category ComboBox | Done
IS6 |  | Add Component Type Label and ComboBox | Done
IS7 |  | Add Quantity | Done
IS8 |  | Add year Installed | Done
IS9 |  | Add Functional Area | Done
IS8FB1 |  | Add Year Installed Renewed does not need Calander / Date picker. Faster for user to type in 4 digits. | Done | 2019-04-13
IS10 |  | Add Not Energy | Done
IS11 |  | Add Painted | Done
IS12 |  | Add Section Comment | Done
IS13 |  | Add Remember | Done
IS14 |  | Add Photos | Done
IS15 |  | Add Photos List | Done
IS16 |  | Add current inspector date | Done
IS17 |  | Add Cancel button | Done
IS18 |  | Add Delete Section button | Done
IS19 |  | Add 'Add Section' button | Done
IS20.FB |  | G: • Supplied you with Add Component and Add Section icons to replace the (identical) placeholders you have used. | Done | 2019-03-31
IS21.FB |  | G: • I will work on place holder icons for Copy Section and Copy Inventory. | Done
IS22.FB |  | G: • Section Name, Equip Cat and Component Type only need a single line - rlh: From the notes it looks like these values cannot be directory edited by the user. Instead, the user selects a member for a list of possibilities. Accordingly, DropDown ComboBox's are being used for these items, not Labels or TextBoxes. | Done | 2019-03-31 | A: Good as is
IS22.FB.2 |  | GD: If there is more than a single section (named N/A) then the user will be able to pick which section to view/edit. NO functionality in Mockup expected. That is for Prototype stage. So for Section, the CAN select from already-existing section names for the current facility OR type in a new Section anme. ComboBox needed. Please do note the Gree Arrow that is a button that the user can tap for quickly cycling through existing sections. In prototype we will suppres that arrow if tehere is only 1 section. The Ma/Equip category is a picklist only. No ability to type in text. FYI: Will present options given the current cComponent type. The Component Tye is also a pickly only. FYI: will present options given the mat/equp category selection in picklist aboce. | Done | 2019-04-18
IS22.1 |  | Need to change Section Name into a combo box. | Done | 2019-04-18
IS22.2 |  | Add more selections to the "Section Name", "Equipment" and "Component" drop-downs. | Done | 2019-04-18
IS22.3 |  | We could hide green arrow on "Sections.Count <= 1" easy enough. | Done | 2019-04-18
IS23.FB |  | G: • The value for DCR Rating are, in order from top to bottom: G+, G G-, Y+, Y, Y-, R+, R, R- (nine possible ratings. Same for P/C ratings. | Done | 2019-04-07
IS24.FB |  | G: Make photo carousel taller in all Views. | Pending | 2019-04-18
IS24.Q1 |  | This is a significant task, leave it as Horizontal list until PT? | Pending | 2019-04-18
IS27.FB |  | Comment section should be soft yellow | Done | 2019-04-03
IS28.FB |  | Calendar DatePicker is too small. Can it be made larger? | Done | 2019-04-18
IS29.FB |  | Section Comment should be soft yellow, not gray | Done | 2019-04-02
IS30 |  | Ask G: Need an image for 'green down button'. | Done | 2019-04-07
IS30.1 |  | Make Green arrow button look the same as on I-Details. | Done | 2019-04-18
IS31 |  | Component Type:' is misspelled. | Done | 2019-04-07
IS32 |  | Green and red plus and minus are buttons that alter the value in the Quantity field | Done | 2019-04-14
IS32.FB1 |  | On the blue button background, the green and red lines are hard to differentiate. Please replace with red pLUS symbol and red MINUS symbol again (that is what users are familiar with) | Done | 2019-04-18
IS32.1 |  | Got the inc/dec working but broke the display. Need to fix! | Done | 2019-04-15 | GD: seem to me it is actually working
IS32.FB2 |  | The MINUS function should not go less than 0. | Done | 2019-04-18
IS33 |  | Ask G: What do the GSF, Footprint and Perimeter buttons do? Change the value in the Qualtity edit? | Closed
IS33FB1 |  | These three are indeed buttons, show as such. | Done | 2019-04-18
IS33FB2 |  | GD: 'The buttons will indeed calculate the quantity and place the result in the Quantity text box. Note: It is NOT expected for this functionality to work in mockup | Closed
IS34 |  | Year Installed edit should be Yellow if Estimated clicked | Done | 2019-04-07
IS35 |  | Ask G: Wireframe has a gray background over the Year P/C items. Should this be reflected in the app? | Done | 2019-04-06 | Answer
IS36 |  | When Section Comment button is clicked show Add/Edit/Delete Comment box | Done | 2019-04-06
IS37 |  | Comment section should be Read Only. No editing allowed. | Done | 2019-04-07
IS38 |  | Click on Section Photo(s) button displays photo editing box. | Done | 2019-04-06
IS38FB1 |  | Photo Button: To launch the Photo Mgmt Popup, not the Camera popup. The Camera popup is lauched from the Photo Mgmt UI. | Done | 2019-04-14
IS39 |  | Add green background to 'Add current inspector' row. | Done | 2019-04-07
IS40 |  | Add Gray background to P/C Rating cells | Done | 2019-04-07
IS41 |  | P/c Rating cells only visible if Painted/Coated checkbox is checked | Done | 2019-04-07
IS42 |  | Make bottom buttons look like WireFrame's. | Done | 2019-04-07
IS43 |  | Year P/C and P/C Type should be in a Gray background box | Done | 2019-04-07
IS44 |  | Hook Cancel Edit button click to an action | Done |  | SKIP in mockup
IS44.Q1 |  | What should this action be? | See IS47FB3
IS45 |  | Hook Delete Section to an action | See IS47FB2
IS46 |  | Hook Add Section to an action | Done
IS47 |  | Ask G: What should Cancel Edit, Delete Section and Add section do? | Done
IS47FB1 |  | Cancel Edit: In mockup no actiuon rqrd | Done
IS47FB2 |  | Add Section: In mockup display Add Section popup | Done
IS47FB3 |  | Delete Section: Standard question confirmation dialog: "Do you want to delete this section and related information? OK / Cancel. No further real action in Mockup | Done | 2019-04-18
| IN | Inspection
IN1 |  | Add Inspection View and ViewModel | Done | 2019-03-31
IN2 |  | Add Component/Section label and remote edit data label | Done | 2019-03-31
IN3 |  | Add Equip Mat. Cat. Label and remote edit data label | Done | 2019-03-31
IN4 |  | Add Component Type label and remote edit data label | Done | 2019-03-31
IN5 |  | Add Section Quantity label, remote edit data label and MBH units label | Done | 2019-03-31
IN6 |  | Add Inspection Date label and DatePicker | Done | 2019-03-31
IN7 |  | Add Inspection Type label and radio buttons Direct Rating and Distress Survey | Done | 2019-03-31
IN7FB1 |  | Add a semi colon after Inspection Type
IN7.1 |  | Direct rating is default. Distress Survey is disabled | Done | 2019-03-31
IN8 |  | Add Painted/Coded label and checkbox | Done | 2019-03-31
IN8FB1 |  | Can we make the "Painted/Coated:" label tap/click sensitive as well, i.e. as if the user is tapping the smallish checkbox for a larger tappable surface? | Done | 2019-04-15
IN9 |  | Add Direct Condition Rating and button grid | Done | 2019-03-31
IN9FB1 |  | second row labels: Green, Amber, Red (i.e. drop the plus sign) third row labels : Green-, Amber-, Red- (i.e. replace + with -_ ) | Done | 2019-04-04
IN9FB2 |  | GD: Background colors are mixed up: G+, G & G-: green background when selected. Y+, Y & Y-: please make yellow (rather than the brownish orange) R+, R & R-: Red background. | Done | 2019-04-18
IN10 |  | Add Paint/Coating Condition Rating label and button grid over blue background | Done | 2019-03-31
IN10FB1 |  | second row labels: Green, Amber, Red (i.e. drop the plus sign) third row labels : Green-, Amber-, Red- (i.e. replace + with -_ ) | Done | 2019-04-04
IN10FB2 |  | GD: Background colors are mixed up: G+, G & G-: green background when selected. Y+, Y & Y-: please make yellow (rather than the brownish orange) R+, R & R-: Red background. | Done | 2019-04-18
IN11 |  | Add Note: Inspection etc label | Done | 2019-03-31
IN12 |  | Add Inspection Comment caption/image over blue BG and multiline editable TextBox | Done | 2019-03-31
IN13 |  | Add Remember checkbox/image over blue background | Done | 2019-03-31
IN14 |  | Add Inspection Photos/image/Qty over blue background plus mock image carousel | Done | 2019-03-31
IN15 |  | Add Cancel Edit and Delete Inspection image buttons | Done | 2019-03-31
IN16.FB |  | First four rows of text boxes | Done | 2019-04-07
IN16.FB.2 |  | soft yellow bg | Done | 2019-04-04
IN16.FB.3 |  | some spacing like you have done on say Facility tab | Done | 2019-04-04
IN17.FB |  | Inspection type: disable Distress Survey radio button | Done | 2019-04-10
IN18.FB |  | Change text color of grid buttons to agree with their captions | Done | 2019-04-06
IN19.FB |  | Once one of the grid buttons has been selected, make its FG black, BG named color and change all other buttons to White over blue | Done | 2019-04-18
IN20 |  | Ask G: Wireframe shows many fields as a light orange instead of gray. What is the significance of this color? | Done
IN20 |  | Ask G: Wireframe shows many fields as a light orange instead of gray. What is the significance of this color? | Done |  | Answer:
IN21 |  | Inspection Date is a little on the narrow side. Make a little wider. | Done | 2019-04-07
IN22 |  | Radio button Distress Survey should be grayed/disabled. | Done | 2019-04-07
IN23 |  | Painted/Coated checkbox is hard to click on with a finger because it has no caption. Fix that. | Done | 2019-04-07
IN23FB1 |  | Please also make the wording in the label responsive, as if checkbox is tapped | Done | 2019-04-20
IN24 |  | Blue color under the right button group is not the client requested color. Fix that. | Done | 2019-04-07
IN25 |  | Clicking on Comment button should display the add/edit/delete comment box. | Done
IN26 |  | No example text in comment box. | Done | 2019-04-20
IN27 |  | Comment box should be Read Only. | Done | 2019-04-20
IN28 |  | Photos row is way too tall. Fix that. | Done | 2019-04-05
IN29 |  | Add sample photos to photo carousel | Done | 2019-04-06
IN30 |  | Make the bottom buttons the same as other Views and compatible with Wireframe | Done | 2019-04-07
L1 | Login | Create View and ViewModel | Done
L1.Q1.1 |  | Add application user strings to contain last configuration and BRED file. Save on Log In click. Restore when Log In displays. See L5. | Done
L2 |  | Blue border and gray BG | Done
L3 |  | Add Build Config caption | Done
L4 |  | Add Build Config TextBox and bind to VM | Done
L5 |  | Save/Retrieve Build Config contents to user sesttings string resources | Done
L6 |  | Add Build Config Select button | Done
L7 |  | Bind Build Config Select button Command to VM | Done
L8 |  | Add BRED caption | Done
L9 |  | Add BRED TextBox | Done
L10 |  | Add BRED Select button | Done
L11 |  | Bind BRED Select button Command to VM | Done
L12 |  | Add Browse dlg to Select Command using saved path | Done |  | Config file is (also) .MDB
L12.Q1 |  | Need to save/retrieve path | SKIP (for PT stage)
L12.Q1.1 |  | See L5. Save to user setting string. | SKIP (for PT stage)
L13 |  | Save/Retrieve last folder to user resources | Done
L14 |  | Add Inspector caption | Done
L15 |  | Add inspector ComboBox | Done
L16 |  | Bind ComboBox Source to VM | Done
L17 |  | VM inspector source populated from config file | Done
L18 |  | ComboBox disabled until source list populated | SKIP (for PT stage)
L19 |  | Add MORE button | Done
L20 |  | Disable MORE until config file read | Done
L21 |  | Bind MORE Command to VM | Done
L21.Q1 |  | What does "More" do? | SKIP (for PT stage) |  | Notes
L22 |  | Add LOGIN button | Done
L23 |  | Disable LOGIN until Config, BRED and Inspector specified | Done
L24 |  | Bind LOGIN Command to VM | Done
L25 |  | LOGIN command closes Login view and displays ShellView | Done
L26 |  | Add Cancel button to terminate application | Done
L27.FB |  | G: 1st line: Builder needs to be all cap: BUILDER Data Collecto | Done | 2019-03-30
L28.FB |  | G: Logo edges look bad. In email I have attached 3 alternatives to try. Be sure to maintain aspect ratio. | Done | 2019-03-30
L28.FB.1 |  | rlh - Replaced the existing logo with a new one. New image is *much* nicer. | Done | 2019-03-30
L29.FB |  | G: • Can we drop all the wasted space on top and bottom, have the soft gray background and (Cardno) dark blue border | Done | 2019-03-30
L30.FB |  | G: • The icons in front of the three text boxes are too small to look good; Either get them bigger or remove. | Done | 2019-03-30
L31.FB |  | G: • The text in the text boxes is too small as well as the 'Inspector is required' message, larger font please. | Partially addressed | 2019-03-30
L31.FB.R1 |  | Increased the text box and combo box font size. However, the validation error string will be a little more difficult. It can be done, just not a trvial change. Will do this later. | Done | 2019-03-30
L31.FB.R3 |  | Let's remover this validation text altogether here. Users will understand they need to pick a name, especially considering the Login button is disabled till they do. | Done | 2019-04-20
L32.FB |  | G: o To note: It is possible that the BRED file to use line can get long; That text box should be auto wrap and expand to two lines of height as needed | Addressed | 2019-03-30
L32.FB.R1 |  | Changed the TextBox from to allow wrapping. When a wrap occurs then the box gets taller to accommodate the text. | Done | 2019-03-30
L33 |  | Need to get rid of main window flash prior to Login display. | Done | 2019-04-20
L34 |  | Change title from Wireframe 1.0 to Mockup 1.0 | Done | 2019-04-14
| QI | QC Inspection
QI1 |  | Add QA View and ViewModel classes | Done | 2019-03-31
QI2 |  | Add buttons | Done | 2019-03-31
QI3 |  | Add data grid | Done | 2019-03-31
QI3FB1 |  | DATA cells that are not selected should be 100% white, not a light shade of gray as it diminishes the contrast between selected and listed/ | Done | 2019-04-20
QI3FB2 |  | Can we use a background color other than gray for the column headers: Soft blue? | Pending | 2019-04-19
QI3.Q2 |  | Ask G: Filter item is orange on the wireframe, not gray. Is this significant? | Pending | 2019-04-19
QI4.FB |  | Tab label: Change QA-Inspection to QC-Inspection | Done | 2019-04-14
QI15 |  | Bug: No toolbar on the View. | Done | 2019-04-20
QI16 |  | Filter and column name are on two separate rows. Fix. | Done
QI16FB1 |  | The two row header design works for me, prevents crouding of the filter icons oner column header, so keep as is! | Closed
QI17 |  | The displayed columns do not agree with the Wireframe's column names. | Done | 2019-04-20
| QV | QC Inventory
QV1 |  | Add QA Inventory View and ViewModel classes | Done | 2019-03-31
QV1FB1 |  | Tab label: Change QA-Inventory to QC-Inventory | Done | 2019-04-14
QV2 |  | Add buttons | Done | 2019-03-31
QV3 |  | Add data grid | Done | 2019-03-31
QV3 |  | Toolbar button row too tall. | Pending | 2019-04-19
QV3.Q1 |  | Is the current size acceptible? | Pending | 2019-04-19
QV3FB1 |  | DATA cells that are not selected should be 100% white, not a light shade of gray as it diminishes the contrast between selected and listed/ | Done | 2019-04-20
QV3FB2 |  | Can we use a background color other than gray for the column headers: Soft blue? | Pending | 2019-04-19
QV3.Q2 |  | Ask G: Filter item is orange on the wireframe, not gray. Is this significant? | Pending | 2019-04-19
QV4FB1 |  | Should be soft yellow to indicate the filter is changeable, but not through editing here, it is done by using the filters for the columns. This area is a summation of filrters in place. | Done
QV5 |  | Bug: Filter and column header text in two separate rows. Fix | Done
QV5FB1 |  | The two row header design works for me, prevents crouding of the filter icons oner column header, so keep as is! | Closed
QV6 |  | Clicking on column header should sort the rows using that column's filter. | Done | 2019-04-20
QV7 |  | Currently active filter should show as green | Done | 2019-04-20
QV8 |  | View's width is much larger than other Views. Is this necessary? If not, fix. | Pending | 2019-04-19
|  | Getting the data grid to both look good and auto-size is proving to be time consuming. A fixed width that suits your expectations is what will do for now. Please specify what size you desire. | Pending | 2019-04-19
QV9 |  | The 'Inventory Issue' filter works in a similar fashion to a 'like' predicate. | Done | 2019-04-20
QV9.1 |  | Implimented a simple "Like" filter. | Done | 2019-04-20
QV10 |  | The 'Inventory Issue' column is misnamed 'InspectionComment Issue'. Fix. | Done | 2019-04-19
| PM | Photo Managerment
PM1 |  | Add View and ViewModel class skeletons. | Done | 2019-03-31
PM2 |  | Add Pending cluster | Done | 2019-04-13
PM3 |  | Add Existing cluster | Done | 2019-04-13
PM4 |  | Add Details cluster | Done | 2019-04-13
PM5 |  | Add Title and Description data collection elements | Done | 2019-04-13
PM5FB |  | The second label should be "Description:" | Done | 2019-04-19
PM6 |  | Connect Shell buttons to show the View | Done | 2019-04-14
PM7 |  | PM displays as a modal dialog | Done | 2019-04-14
PM8 |  | Title is populated with the name of the tab that launched the PM plus information about what is being displayed | Done | 2019-04-19
PM9 |  | Add a command handler to Capture Photo button to start a message box | Done | 2019-04-14
PM10 |  | Add a command handler to Select Photo button to start a file browser | Done | 2019-04-14
PM10.1 |  | Content of file browser are added to the Pending ListBox | Done | 2019-04-14
PM11 |  | Add a command handler to Add All Pending to copy contents of Pending to Existing list | Done | 2019-04-14
PM12 |  | Add a command handler to Remove Selected to remove selected item from Existing list | Done | 2019-04-14
PM13 |  | Populate Existing ListBox | Done | 2019-04-14
PM14 |  | Unlink Existing Photo closes PM | Done | 2019-04-14
PM15 |  | On successful return, the contents of Existing Photo list replace the caller's photo list. | Skipped, implimented in PT | 2019-04-19
PM15.Q1 |  | Ask G: How to return without replacing the photolist? Add a Cancel Button? | Closed
PM15.FB1 |  | No cancel required; the user can unlink a photo if linked in error. (Rare) | Closed
PM15.Q2 |  | Ask G: How to close the PM View with an indication that changes made should be applied? OK button? | Done | 2019-04-19
PM15.FB2 |  | Sounds good: An OK button on the same row as Unlink, to the right, centered if possible so it does not appear related to linking/unlinking. (In addition, the user can tap the X of the window off course) | Done | 2019-04-19
| Shell | The Shell is the main window itself which contains the various tabs, trees and so on.
S1 |  | Create ShellView and ShellViewModel | Done
S2 |  | Bind Title to VM | Done
S3 |  | Title string constructed from Build DC + pathname of a file | Done
S3.Q2 |  | Ask G: What data is stored in the BRED file? | Done |  | PT Notes
S3.Q3 |  | G: What data is stored in the config file?Ask | Done |  | PT Notes
S4 |  | Add Menu | Done
S5 |  | Add Submenus | Done
S5.FB1 |  | View Assigned Systems should have a checkmark in front. If the user clicks the View All Systems, then the checkmark should move here. They are an mutually-exclusive pair. PT: Remembered for duration of session only. | Done | 2019-04-13
S5FB2 |  | Reports ¦ InspectionComment Summary > Inspection Summary | Done | 2019-03-04
S6 |  | Add Toolbar | Done
S7 |  | Add buttons to Toolbar | Done
S8 |  | Add TreeView | Done
S8.FB1 |  | In treeview bogus data, change ARMRY to "11507 - National Guard Readiness Center" and change GILLS to "11444 - Facility # 2" | Done | 2018-04-17
S9 |  | Bind TreeView source to ShellViewModel | Done
S10 |  | Details TreeView to all expanded | Done
S10.Q1 |  | Ask G: Need better definition of tree items / filters. | Done
|  | GD: Filtering will exist, but is outside of Mockup scope (because it requires reading project configuration data) Treeview nodes display depends on the mode the user is in: Inventory (tree) Mode (default) or Inspection (tree) Mode (these are the two left-most icons on toolbar) For details see spreadsheet BDC Treeview details_S10.Q1.xlsx | Closed | 2019-04-19
S11 |  | Bind selected TreeView item to VM | Done
S12 |  | Add grid splitter | Done
S13 |  | Add TabView | Done
S14 |  | Add Status Bar | Done
S15 |  | Add Status Bar contents and bind to ShellViewModel | Done
S17.FB |  | Misunderstanding. Those are sub menu items, not another toolbar. Remove from Shell. | Done | 2019-03-30
S17.FB.1 |  | Removed the spurious Toolbar and updated the remaining one. | Done | 2019-03-30
S18.FB1 |  | Make title bar font bigger by approx 20% | Skipped | 2019-03-30
S18.FB1.1 |  | This is possible but not trivial. Will delay implementation until after more functional things have been completed. | Skipped
S18.FB3 |  | Given that it is not trivial, let's forget about changing the font size of Window title bars. | Done
S18.FB2 |  | G: Let's move the BRED file name to the Status bar on the bottom instead. Make status bar two rows? Increase the font size of the status bar for both rows. | Done | 43568
S19.FB |  | Make menu text bigger | Done | 2019-03-30
S20.FB |  | Make toolbar taller with more space between menu and below. | Done | 2019-03-30
S21.FB |  | Build (aka Inventory) and Inspection icons should both be present with some means of indicating what mode currently in, Inventory or Inspect. | Pending
S21.FB.1 |  | Added the toolbar buttons but 'currently selected' indication is not yet implemented | In process | 2019-03-30
S22.FB1 |  | Add system and Delete system icons. As we need to distinguish adding system from adding component from adding Section, I have created three simplistic placeholder PNG files to use as toolbar images. Same thing for delete. | Done | 2019-04-04
S22.FB1.1 |  | Ask G: The 'add system and delete system icon' thing is a little confusing. Can you elaborate on that? | Done | 2019-03-30 | PT Notes
S22.FB1.2 |  | G: Clicking the Sys+ button is to bring up what yo see on the Sys+ tab in the wireframe. For Sys-, simpley create function place holder and display placeholder dialog: "Do you want to delete the currently selected System for Facility ####?" | Done
S22.FB1.3 |  | Implemented something closer to the real thing. | Done | 2019-04-04
S23 |  | Modify the Tab item style to be fat finger compatible and more colorful on selection. | Done | 2019-04-04
S23.1 |  | Add space between Tabs | Done | 2019-04-04
S23.2 |  | Make selected tab colorful | Done | 2019-04-17
S23.2.1 |  | Not happy with color. Needs more work | Done | 2019-04-04 | Good Enough!
S24 |  | Remember and reassert window placement between sessions | Done | 2019-03-31
S25 |  | Bug: Before Login shows, the Shell briefly flashes. It should not. | Done | 2019-03-31
S26 |  | Wireframe shows tabs as a series of different blue shades. | Done | 2019-04-04 | Good Enough!
S27 |  | Update Copy, Add and Delete functions with new/replacement PNG files which have been supplied in BDC_75x75.zip | Done | 2019-04-13
S27.1 |  | New images have been applied | Done | 2019-04-13
S28 |  | The difference in color of the last two tab headers needs to be greater. Make the last much darker blue. | Done | 2019-04-13
S28.1 |  | Colors adjusted. Good enough? | Pending | 2019-04-20
Toolbar
T1 |  | Add buttons that show and hide depending upon the currently active tab control | Done | 2019-03-30
T1.FB1 |  | Please make the toolbar background gray a bit lighter (so better contrast of the black letters on the icons) | Done | 2019-04-17
T2 |  | Ask G for an image for Copy Inventory button | Done | 2019-04-13
T3 |  | Ask G for an image for Copy Inspection button | Pending | 2019-03-31
T3.Q1 |  | No Copy Inspection image supplied with the last delivery. Still Pending? | Pending
T4 |  | Ask G for an image for Copy Sections button | Done | 2019-04-13
T5 |  | Inventory Mode tooltip: "Inventory Mode" | Done | 2019-03-13
T6 |  | Inspection Mode tooltip: "Inventory Mode" | Done
T6.FB |  | The tooltips are correct as they are now. | Done
T6.Q1 |  | Inventory Mode'? Not 'Inspection Model'? | Done | 2019-03-13
|  | Total Tasks: | 413
|  | Done / Closed: | 387 | 93.7%
|  | In Process: | 1 | 0.2421%
|  | Pending: | 18 | 4.358%
|  | Remaining: | 7 | 1.695%
Note on F138: George 'Jos' Durtler: : from the BRED file, so you have it correctly shown with gray background
Note on F179: George 'Jos' Durtler: PT: This will launch a barcode reading popup, essentially a rectangle within which the user sees live image from camera to help position the rectangle around the barcode to read. As the code type is recognized and read, there will be a beep and the value displayed. The user clicks OK and the value is transferred, the popup closes. If the wrong barcode was grabbed, the user can reposition camera and try again. I have selected an open source .NET/C# app for this to use.
Note on F180: George 'Jos' Durtler: PT: The (#) indicator in the Details sub tab indicates ther number of existing Details for this section. Example: The component 'BOILER' can actually have 1 or more boilers which are each to have their own details.
Note on F190: George 'Jos' Durtler: BDC's default behavior is to automatically save all additions/edits UNLESS the user clicks Cancel Edit. Reason: Most actions are Save, rarely to Cancel. Nothing more to do in Mockup
Note on F204: George 'Jos' Durtler: If System starts with D or E, then Equipment Category, else Material Category
Note on F246: George 'Jos' Durtler: Design-wise, wanted to make clear to user that that area is P/C specific. Gray as you have it is fine, does the job. One request is to use the top row of that gray area to add label: Painted/Coated Info: (see latest wireframe spec)
Note on F299: George 'Jos' Durtler: My bad: Should be soft yellow background (as they are controllable in BDC, just not in that spot (i.e. are done on the Inventory tab). (Remember: light gray background is for data that can not be changed by user anywhere, i.e. is from the original BRED file and is FYI for the user.
Note on F341: George 'Jos' Durtler: The pulldown list is normally to be used. It will have all intended users listed for this project, and thus be a short list, typically 4 - 20. In the Project Config 'PC' file. The More button will retrieve a longer list of possible users retrieved from the BRED file, justed just in case the user was omitted during project setup.
Note on F436: George 'Jos' Durtler: PT: BRED file: Actual data being collected/edited by the inspector. Data describes facilities, inventory, inspections. (Excl. photos)
Note on F437: George 'Jos' Durtler: PT: Project Config file, an MDB file as well, contains project-specific information and is shared by all inspectors on a project. Examples: Photo nmainig convention, photo resolution required, who are the users on the project, what their assignments are.
Note on F467: George 'Jos' Durtler: PT: In our parlance, a System is a high-level classification consisting of a letter and 2 digits. Example: B#0 is a System. All systems that require inspection should be in the starting BRED file, but just in case, Add and delete System functionality will let the user make a change. Example: D30, HVAC was missing in the file and it turns out the facility does have HVAC, so the inspector is to add it.

## Gen Ques
ID | Area | Task | Status | Last Activity | Notes
| GC | General Questions
GC.Q1 |  | Do we need to make custom "Message Box" for thoses single-line questions? It's related to that whole "fat-fingers" style. There are some Material-Design concepts we could use. Here are some examples
GC.Q1.FB.1 |  | https://github.com/denpalrius/Material-Message-Box

## Add New Component
ID | Area | Task | Status | Last Activity | NOTES
| AC | Add New Component
AC1 | AC | Add View and ViewModel class skeletons. | Done | 2019-03-31
AC2 | AC | Add label, combo and buttons to View | Done | 2019-03-31
AC3 | AC | Connect OK and Cancel buttons to ViewModel
AC4 | AC | Connect Shell buttons to show the View

## Add System
ID | Area | Task | Status | Last Activity | NOTES
| AS | Add System
AS1 | AS | Add View and ViewModel class skeletons. | Done | 2019-03-31
AS2 | AS | Add label, combo and buttons to View | Done | 2019-03-31
AS3 | AS | Connect OK and Cancel buttons to ViewModel
AS4 | AS | Connect Shell buttons to show the View

## Application
ID | Area | Task | Status | Last Activity | NOTES
| App | Application
A1 | App | Add left justified Label style | Done
A2 | App | Add center justified Label style | Done
A3 | App | Add right justified Label style | Done
A4 | App | Add bold Label stytle | Done
A5 | App | Add gray BG black bounded Label style | DOne

## Bluebeam
ID | Area | Task | Status | Last Activity | NOTES
Bluebeam
B1.Q | Bluebeam | G: What is this? Need direction on this. | Ask G | 2019-03-31
B1.Q2 | Bluebeam | GD: Trigger a File Open dialog. File type: XLSX, Caption: "Select Bluebeam Excel file (placeholder)" OK/Cancel buttons. Nothing is expected to happen in the mockup regardless what spreadsheet the user may/may not select. FYI only: In prototype stage, we will read data in spreadsheet and present as text in the window that you can see in the wireframe, Main tab, Cells M8- S27.

## Copy Comment
ID | Area | Task | Status | Last Activity | NOTES
CC1 | CC | Add View and ViewModel class skeletons. | Done | 2019-03-31
CC1FB1 | CC | Larger, matching fonts to other areas
CC1FB2 | CC | Label My Saved Com > My saved comments
CC1FB3 | CC | Label ComponentFacility > Facility:
CC1FB4 | CC | Lab el ComponentInvents > Component Type:
CC1FB5 | CC | Label Yellow > Green
CC1FB6 | CC | data rows not selected: white Backgrouns (for contrast)
CC1FB7 | CC | Increase height: near double so we can show a lot more comments without user having to page. Also double width, giving the extra space to the comment column
CC1FB8 | CC | The comment colum will need to wrap, so user can see full comment text, expanding row height as needed, if possible. If not, set aside two rows of text per comment.
CC2 | CC | Add Source row | Done | 2019-03-31
CC3 | CC | Add Related to current row | Done | 2019-03-31
CC4 | CC | Add Rated as row | Done | 2019-03-31
CC5 | CC | Add Search term row | Done | 2019-03-31
CC6 | CC | Add Facility code DCR Comment data grid | Done | 2019-03-31
CC7 | CC | Add bottom button row | Done | 2019-03-31
CC8 | CC | Connect Shell buttons to show the View

## Comment on Inspection
ID | Area | Task | Status | Last Activity | NOTES
| CI | Comment on Inspection
CI1 | CI | Add View and ViewModel class skeletons. | Done | 2019-03-31
CI2 | CI | Add toolbar and connect images to each button | Done | 2019-03-31
CI3 | CI | Add radio buttons
CI3 | CI | The No Recomm. Radio button is default, please spell out: No recommendation.
Font size: larger to match other Uis done
CI4 | CI | Create a style for radio buttons so that they match the spec
CI5 | CI | Connect Inspection's 'Inspection Comment' button to launch popup.

## Comment Popup
ID | Area | Task | Status | Last Activity | NOTES
| CM | Comment Popup
CM1 | CM | Add View and ViewModel class skeletons | Done | 2019-03-31
CM2 | CM | Add toolbar and connect images to each button | Done | 2019-03-31
CM3 | CM | Get more info on what data and controls are in the View from G.
CM4 | CM | Ask G to clarify, what launches the Comment Popup? | Closed
CM5 | CM | Connect Shell buttons to show the View
CM6 | CM | Update the Title depending upon what comment is being updated
CM7 | CM | Ask G: Where does <IDENTIFIER CONTINUEED> come from?
CM7FB1 | CM | GD: This gray background area reinforces exactly which comment the user is working on, <CONTINUED> is a wrap-artound continuation of the first gray row. For example and structure see the WF, Cm tab, areas L4 - S8
CM8 | CM | Ask G: How does Delete work? What triggers a delete of the current comment?
CM8FB1 | CM | GD: There is no delete here because clearing all text is a sign for BDC to set the comment to NULL
CM9 | CM | Ask G: What is 'auto stamping'?
CM9FB1 | CM | GD: PT -- Identifies inspector and date/time in a standardized format. See explanation on Cm tab, cells L12 - T16

## Copy Inventory
ID | Area | Task | Status | Last Activity | NOTES
| CN | Copy Inventory
CN1 | CN | Add View and ViewModel class skeletons. | Done | 2019-03-31
CN1FB1 | CN | Label Copy InspectionComments > Copy Inspections
CN1FB2 | CN | Larger font, similar to used elsewhere.
CN1FB3 | CN | Year text cell to be just large enough for 5 digits (the 5th being a mistake)
CN2 | CN | Add Source Facility row
CN3 | CN | Add Target Facility row
CN4 | CN | Add Section Name row
CN5 | CN | Add Systems to copy rows
CN6 | CN | Add Options cluster
CN7 | CN | Add bottom button row
CN8 | CN | Connect Shell buttons to show the View

## Capture Photo
ID | Area | Task | Status | Last Activity | NOTES
| CP | Camera UI/Capture Photo
CP1 | CP | Add View and ViewModel class skeletons. | Done | 2019-03-31
CP2 | CP | Add toolbar and buttons | Done | 2019-03-31
CP2FB1 | CP | GD: Need fpor photo size control has been deleted from spec. Please remove those three items
CP2FB2 | CP | GD: For energy conservation, need to provide users control over flash usage, preference is off. These are a set, i.e. to indicate which mode is on.
CP3 | CP | Add Image area | Done | 2019-03-31
CP3FB1 | CP | Please increase in size to show a 800 x 600 pixel photo plus surroundings of course. Note: 800 x 600 is the standard photo size in BUILDER projects, so 100% represnertative of what end users will see eventually.
CP4 | CP | Connect Cancel and OK buttons
CP5 | CP | Customize toolbar button appearance
CP6 | CP | Connect Shell buttons to show the View

## Facility
ID | Area | Task | Status | Last Activity | NOTES
Facility
F1 | Facility | Add Facility View and ViewModel | Done | 2019-03-29
F2 | Facility | Add 'Identity' items | Done | 2019-03-29
F3 | Facility | Add 'Faility Comment' TextBox | Done | 2019-03-29
F4 | Facility | Add 'Photos thumbnails' Listbox | Done | 2019-03-29
F4.Q1 | Facility | Picture carousel is a hard coded script, not a true carousel. | Done | 2019-03-29
F5 | Facility | Add 'Address' items | Done | 2019-03-29
F6 | Facility | Add 'Point of contact' items | Done | 2019-03-29
F7.FB | Facility | Need more space between Alt ID and Facility comment section | Done | 2019-03-31
F8.FB | Facility | Need more space between Facility comment and Photo carousel. | Done | 2019-03-31
F9.FB | Facility | The text box for Quantity is too small: should accommodate 888,888.88 You can adjust Building ID, Year built and Alternate ID to be the same, as shown in the wire frame. | Done | 2019-04-02
F10.FB | Facility | Address section: No need for 2nd address line, please remove | Done | 2019-04-01
F11.FB | Facility | Comment with light yellow background rather than orange please, BDC’s standard for text that can be edited but not where displayed. | Done | 2019-04-02
F12.FB | Facility | In this 3rd iteration, somehow cells that were light gray background are showing up as white again. | Done | 2019-04-02
F13.FB | Facility | Only ones that should have white background are ones the user can edit: Width, Depth and Floor Height | Done | 2019-04-02
F13.FB.1 | Facility | Ask G: What about Quantity? Where does its data come from? | Pending |  | Answer
F14 | Facility | Bug: Width, Depth and Floor Height should be editable but are not. | Fixed | 2019-04-03
F15 | Facility | Photo Button: To launch the Photo Mgmt Popup, not the Camera popup. The Camera popup is lauched from the Photo Mgmt UI.
Note on F17: George 'Jos' Durtler: : from the BRED file, so you have it correctly shown with gray background

## General
ID | Area | Task | Status | Last Activity | NOTES
| General | This section is concerned with tasks that relate to general
G1.FB | General | G: • Text boxes in general: Too much space above and below the text, uses up a lot of valuable vertical space.
G2 | General | DatePicker's vertical text alignment is Top. Can it be changed to Center?

## Inventory
ID | Area | Task | Status | Last Activity | NOTES
Inventory
I1 | Inventory | Add Inventory View and ViewModel | Done
I2 | Inventory | Add Tab control | Done
I3 | Inventory | Add color to Tab control | Done | 2013-04-06

## I-Detail
ID | Area | Task | Status | Last Activity | NOTES
| I-Detail | Inventory Details
ID1 | I-Detail | Add InventoryDetails View and ViewModel | Done
ID2 | I-Detail | Add Current Section label and a read only data label | Done
ID3 | I-Detail | Add Detail Selector caption and dropdown list combobox | Done
ID4 | I-Detail | Add green BG to Current Section and Detail Selector caption labels | Done | 2019-04-07
ID5 | I-Detail | Add Detail ID and Location label and data TextBox | Done
ID6 | I-Detail | Add Model and Serial Number label and data TextBox | Done
ID7 | I-Detail | Add Manufacturer label and data ComboBox | Done
ID7.Q.1 | I-Detail | Ask G: Pick list or can user type in a value? |  |  | Combo: Select or Type in
ID8 | I-Detail | Add Capacity label and data TextBox | Done
ID9 | I-Detail | Add Equipment Type label and data TextBox | Done
ID10 | I-Detail | Add Equip. Make and ComboBox | Done
ID10.Q.1 | I-Detail | Ask G: Pick list or can user type in a value? |  |  | Combo: Select or Type in
ID11 | I-Detail | Add Date Manufactured label and DatePicker | Done
ID12 | I-Detail | Add Year Installed and data TextBox | Done
ID13 | I-Detail | Add Control Type/Make label and data TextBox | Done
ID14 | I-Detail | Add Warranty Date label and DatePicker | Done
ID15 | I-Detail | Add Warranty Company and data TextBox | Done
ID16 | I-Detail | Add Warranty Date 2 label and DatePicker | Done
ID17 | I-Detail | Add Warranty Company 2 label and data TextBox | Done
ID18 | I-Detail | Add Detail Command image, blue background label and Comment field which is edited elsewhere | Done
ID19 | I-Detail | Add mocked Detail Photos image carousel | Done
ID20 | I-Detail | Add Cancel Edit, Delete Detail, Add Detail and Copy Detail image buttons | Done
ID20.FB | I-Detail | Relocate ID20's buttons so that all are on the same row | Done | 2019-04-03
ID21.FB | I-Detail | Detail Comment should be soft yellow, not gray | Done | 2019-04-02
ID22.FB | I-Detail | G: Green arrow next to Detail Selector is missing. Add it. | Done | 2019-04-03
ID23.FB | I-Detail | G: The barcode image is actually a command button | Done | 2019-04-07
ID23.FB.2 | I-Detail | Ask G: what does the barcode button do? | Closed
ID23.FB.3 | I-Detail | Ask G: Barcode button launches a barcode reader. Where is this reader? | Done (impl in PT) |  | PT Answer
ID24 | I-Detail | Ask G: What is the (#)? |  |  | PT Answer
ID25 | I-Detail | Curent Section and Detail Selector cells are supposed to have a green background.
ID26 | I-Detail | Add green down button to Current Selector. | Done | 2019-04-07
ID27 | I-Detail | Click on green down button increments through the list in the associated combo. | Done | 2019-04-07
ID28 | I-Detail | Bug: Warr. Company 2: doesn't have a 2. | Done | 2019-04-07
ID29 | I-Detail | Detail Comment button should bring up Add/Edit/Delete comment box when clicked. | Done | 2019-04-06
ID30 | I-Detail | Comment should be Read Only. | Done | 2019-04-07
ID31 | I-Detail | Click on Detail Photos button should bring up photo adder/editor box. | Done | 2019-04-06
ID31FB1 | I-Detail | Photo Button: To launch the Photo Mgmt Popup, not the Camera popup. The Camera popup is lauched from the Photo Mgmt UI.
ID32 | I-Detail | Make bottom buttons look like wireframe's. | Done | 2019-04-07
ID33 | I-Detail | Ask G: How should a click on 'Cancel Edit' work? | Done |  | Answer
ID34 | I-Detail | Ask G: How should a click on 'Delete Detail' work?
ID34FB1 |  | present dialog: "Are you sure you want to delete current section and related info?" OK / Cancel. (real action beyond that is for PT)
ID35 | I-Detail | Ask G: How should Add Detail work? |  |  | PT Answer
ID36 | I-Detail | Ask G: How should Copy Detail work? |  |  | PT Answer
Note on F30: George 'Jos' Durtler: PT: This will launch a barcode reading popup, essentially a rectangle within which the user sees live image from camera to help position the rectangle around the barcode to read. As the code type is recognized and read, there will be a beep and the value displayed. The user clicks OK and the value is transferred, the popup closes. If the wrong barcode was grabbed, the user can reposition camera and try again. I have selected an open source .NET/C# app for this to use.
Note on F31: George 'Jos' Durtler: PT: The (#) indicator in the Details sub tab indicates ther number of existing Details for this section. Example: The component 'BOILER' can actually have 1 or more boilers which are each to have their own details.
Note on F41: George 'Jos' Durtler: BDC's default behavior is to automatically save all additions/edits UNLESS the user clicks Cancel Edit. Reason: Most actions are Save, rarely to Cancel. Nothing more to do in Mockup
Note on F44: George 'Jos' Durtler: PT: This will save current detail addition/changes if any and present the same UI with blank fields for the user to enter the details for the 2nd detail, and so on.
Note on F45: George 'Jos' Durtler: PT: will work like Add New Detail function, but will copy over the values of the current detail to the new detail. Used whenever the items (= details) are very similar to each other. Example: multiple boilers from the same type, mfg, etc. Objective: faster to edit a few choice fields than start from scratch in that case.

## I-Section
ID | Area | Task | Status | Last Activity | NOTES
| I-Section | Inventory Section
IS1 | I-Section | Add InventorySection View and ViewModel | Done
IS1 FB1 | I-Section | Details sub tab: Don't use bright yellow for background. Maybe also a shade of orange like the Section sub tab?
IS2 | I-Section | Add Section Name list control | Done
IS3 | I-Section | Add Section ComboBox | Done
IS4 | I-Section | Add Equipment Category caption and bind to VM which changes | Done
IS4.Q1 | I-Section | G: What are the rules for Category caption change? | See Answer |  | Answer
IS4.Q1.1 | I-Section | GD: If current selected node in treeview has System starting with D or E then 'Equiment Category', all others 'Material Category'. | Pending
IS5 | I-Section | Add Category ComboBox | Done
IS6 | I-Section | Add Component Type Label and ComboBox | Done
IS7 | I-Section | Add Quantity | Done
IS8 | I-Section | Add year Installed | Done
IS8FB1 | I-Section | Add Year Installed Renewed does not need Calander / Date picker. Faster for user to type in 4 digits.
IS9 | I-Section | Add Functional Area | DOne
IS10 | I-Section | Add Not Energy | Done
IS11 | I-Section | Add Painted | Done
IS12 | I-Section | Add Section Comment | Done
IS13 | I-Section | Add Remember | Done
IS14 | I-Section | Add Photos | Done
IS15 | I-Section | Add Photos List | Done
IS16 | I-Section | Add current inspector date | Done
IS17 | I-Section | Add Cancel button | Done
IS18 | I-Section | Add Delete Section button | Done
IS19 | I-Section | Add 'Add Section' button | Done
IS20.FB | I-Section | G: • Supplied you with Add Component and Add Section icons to replace the (identical) placeholders you have used. | Done | 2019-03-31
IS21.FB | I-Section | G: • I will work on place holder icons for Copy Section and Copy Inventory.
IS22.FB | I-Section | G: • Section Name, Equip Cat and Component Type only need a single line - rlh: From the notes it looks like these values cannot be directory edited by the user. Instead, the user selects a member for a list of possibilities. Accordingly, DropDown ComboBox's are being used for these items, not Labels or TextBoxes. | Possible misunderstanding. Need to ask G. Waiting for response | 2019-03-31 | A: Good as is
IS22.FB.2 | I-Section | GD: PT: If there is more than a single section (named N/A) then the user will be able to pick which section to view/edit. NO functionality in Mockup expected. That is for Prototype stage. So for Section, the user CAN select from already-existing section names for the current facility OR type in a new Section anme. ComboBox needed. Please do note the Gree Arrow that is a button that the user can tap for quickly cycling through existing sections. In prototype we will suppres that arrow if tehere is only 1 section. The Ma/Equip category is a picklist only. No ability to type in text. FYI: Will present options given the current cComponent type. The Component Tye is also a pickly only. FYI: will present options given the mat/equp category selection in picklist aboce. | Done
IS23.FB | I-Section | G: • The value for DCR Rating are, in order from top to bottom: G+, G G-, Y+, Y, Y-, R+, R, R- (nine possible ratings. Same for P/C ratings. | Done | 2019-04-07
IS24.FB | I-Section | G: Make photo carousel taller in all Views.
IS27.FB | I-Section | Comment section should be soft yellow | Done | 2019-04-03
IS28.FB | I-Section | Calendar DatePicker is too small. Can it be made larger?
IS29.FB | I-Section | Section Comment should be soft yellow, not gray | Done | 2019-04-02
IS30 | I-Section | Ask G: Need an image for 'green down button'. | Closed | 2019-04-07
IS31 | I-Section | Component Type:' is misspelled. | Done | 2019-04-07
IS32 | I-Section | Ask G: What do the green + and red - do? Inc/Dec Quantity by 1? | Pending | 2019-04-02 | PT Notes
IS33 | I-Section | Ask G: What do the GSF, Footprint and Perimeter buttons do? Change the value in the Qualtity edit? | Pending | 2019-04-02 | PT Notes
IS33FB1 | I-Section | These three are indeed buttons, show as such.
IS34 | I-Section | Year Installed edit should be Yellow if Estimated clicked | Done | 2019-04-07
IS35 | I-Section | Ask G: Wireframe has a gray background over the Year P/C items. Should this be reflected in the app? | Pending | 2019-04-06 | Answer
IS36 | I-Section | When Section Comment button is clicked show Add/Edit/Delete Comment box | Done | 2019-04-06
IS37 | I-Section | Comment section should be Read Only. No editing allowed. | Done | 2019-04-07
IS38 | I-Section | Click on Section Photo(s) button displays photo editing box. | Done | 2019-04-06
ID38FB1 | I-Section | Photo Button: To launch the Photo Mgmt Popup, not the Camera popup. The Camera popup is lauched from the Photo Mgmt UI.
IS39 | I-Section | Add green background to 'Add current inspector' row. | Done | 2019-04-07
IS40 | I-Section | Add Gray background to P/C Rating cells | Done | 2019-04-07
IS41 | I-Section | P/c Rating cells only visible if Painted/Coated checkbox is checked | Done | 2019-04-07
IS42 | I-Section | Make bottom buttons look like WireFrame's. | Done | 2019-04-07
IS43 | I-Section | Year P/C and P/C Type should be in a Gray background box | Done | 2019-04-07
IS44 | I-Section | Hook Cancel Edit button click to an action | SKIP in mockup |  | This is for PT stage
IS45 | I-Section | Hook Delete Section to an action | See IS47FB3
IS46 | I-Section | Hook Add Section to an action | See IS47FB2
IS47 | I-Section | Ask G: What should Cancel Edit, Delete Section and Add section do?
IS47FB1 | I-Section | Cancel Edit: In mockup no actiuon rqrd
IS47FB2 | I-Section | Add Section: In mockup display Add Section popup
IS47FB3 | I-Section | Delete Section: Standard question confirmation dialog: "Do you want to delete this section and related information? OK / Cancel. No further real action in Mockup
Note on F8: George 'Jos' Durtler: If System starts with D or E, then Equipment Category, else Material Category
Note on F37: George 'Jos' Durtler: These increment Qty field by 1 or decrement by 1.
Note on F38: George 'Jos' Durtler: PT: Correct, they will overwrite the Qty text box value based on simple formulas derived from facility properties on the Facility tab.
Note on F41: George 'Jos' Durtler: Design-wise, wanted to make clear to user that that area is P/C specific. Gray as you have it is fine, does the job. One request is to use the top row of that gray area to add label: Painted/Coated Info: (see latest wireframe spec)

## Inspection
ID | Area | Task | Status | Last Activity | NOTES
| INSP | Inspection
IN1 | INSP | Add Inspection View and ViewModel | Done | 2019-03-31
IN2 | INSP | Add Component/Section label and remote edit data label | Done | 2019-03-31
IN3 | INSP | Add Equip Mat. Cat. Label and remote edit data label | Done | 2019-03-31
IN4 | INSP | Add Component Type label and remote edit data label | Done | 2019-03-31
IN5 | INSP | Add Section Quantity label, remote edit data label and MBH units label | Done | 2019-03-31
IN6 | INSP | Add Inspection Date label and DatePicker | Done | 2019-03-31
IN7 | INSP | Add Inspection Type label and radio buttons Direct Rating and Distress Survey | Done | 2019-03-31
IN7.1 | INSP | Direct rating is default. Distress Survey is disabled | Done | 2019-03-31
IN8 | INSP | Add Painted/Coded label and checkbox | Done | 2019-03-31
IN9 | INSP | Add Direct Condition Rating and button grid | Done | 2019-03-31
IN9FB1 | INSP | second row labels: Green, Amber, Red (i.e. drop the plus sign) third row labels : Green-, Amber-, Red- (i.e. replace + with -_ )
IN10 | INSP | Add Paint/Coating Condition Rating label and button grid over blue background | Done | 2019-03-31
IN10FB1 | INSP | second row labels: Green, Amber, Red (i.e. drop the plus sign) third row labels : Green-, Amber-, Red- (i.e. replace + with -_ )
IN11 | INSP | Add Note: Inspection etc label | Done | 2019-03-31
IN12 | INSP | Add Inspection Comment caption/image over blue BG and multiline editable TextBox | Done | 2019-03-31
IN13 | INSP | Add Remember checkbox/image over blue background | Done | 2019-03-31
IN14 | INSP | Add Inspection Photos/image/Qty over blue background plus mock image carousel | Done | 2019-03-31
IN15 | INSP | Add Cancel Edit and Delete Inspection image buttons | Done | 2019-03-31
IN16.FB | INSP | First four rows of text boxes | Done | 2019-04-07
IN16.FB.2 | INSP | soft yellow bg | Done
IN16.FB.3 | INSP | some spacing like you have done on say Facility tab | Done
IN17.FB | INSP | Inspection type: disable Distress Survey radio button | Done
IN18.FB | INSP | Change text color off grid buttons to agree with their captions | Done | 2019-04-06
IN19.FB | INSP | Once one of the grid buttons has been selected, make its FG black, BG named color and change all other buttons to White over blue
IN20 | INSP | Ask G: Wireframe shows many fields as a light orange instead of gray. What is the significance of this color? |  |  | Answer:
IN21 | INSP | Inspection Date is a little on the narrow side. Make a little wider. | Done | 2019-04-07
IN22 | INSP | Radio button Distress Survey should be grayed/disabled. | Done | 2019-04-07
IN23 | INSP | Painted/Coated checkbox is hard to click on with a finger because it has no caption. Fix that. | Done | 2019-04-07
IN23FB1 | INSP | Please also make the wording in the label responsive, as if checkbox is tapped
IN24 | INSP | Blue color under the right button group is not the client requested color. Fix that. | Done | 2019-04-07
IN25 | INSP | Clicking on Comment button should display the add/edit/delete comment box.
IN26 | INSP | No example text in comment box.
IN27 | INSP | Comment box should be Read Only.
IN28 | INSP | Photos row is way too tall. Fix that. | Done | 2019-04-05
IN29 | INSP | Add sample photos to photo carousel | Done | 2019-04-06
IN30 | INSP | Make the bottom buttons the same as other Views and compatible with Wireframe | Done | 2019-04-07
Note on F27: George 'Jos' Durtler: My bad: Should be soft yellow background (as they are controllable in BDC, just not in that spot (i.e. are done on the Inventory tab). (Remember: light gray background is for data that can not be changed by user anywhere, i.e. is from the original BRED file and is FYI for the user.

## Login
ID | Area | Task | Status | Last Activity | NOTES
L1 | Login | Create View and ViewModel | Done
L1.Q1.1 | Login | Add application user strings to contain last configuration and BRED file. Save on Log In click. Restore when Log In displays. See L5. | Done
L2 | Login | Blue border and gray BG | Done
L3 | Login | Add Build Config caption | Done
L4 | Login | Add Build Config TextBox and bind to VM | Done
L5 | Login | Save/Retrieve Build Config contents to user sesttings string resources | Done
L6 | Login | Add Build Config Select button | Done
L7 | Login | Bind Build Config Select button Command to VM | Done
L8 | Login | Add BRED caption | Done
L9 | Login | Add BRED TextBox | Done
L10 | Login | Add BRED Select button | Done
L11 | Login | Bind BRED Select button Command to VM | Done
L12 | Login | Add Browse dlg to Select Command using saved path |  |  | Config file is (also) .MDB
L12.Q1 | Login | Need to save/retrieve path
L12.Q1.1 | Login | See L5. Save to user setting string.
L13 | Login | Save/Retrieve last folder to user resources | Done
L14 | Login | Add Inspector caption | Done
L15 | Login | Add inspector ComboBox | Done
L16 | Login | Bind ComboBox Source to VM | Done
L17 | Login | VM inspector source populated from config file | Done
L18 | Login | ComboBox disabled until source list populated
L19 | Login | Add MORE button | Done
L20 | Login | Disable MORE until config file read | Done
L21 | Login | Bind MORE Command to VM | Done
L21.Q1 | Login | What does "More" do? | Ask G. > see notes |  | Notes
L22 | Login | Add LOGIN button | Done
L23 | Login | Disable LOGIN until Config, BRED and Inspector specified | Done
L24 | Login | Bind LOGIN Command to VM | Done
L25 | Login | LOGIN command closes Login view and displays ShellView | Done
L26 | Login | Add Cancel button to terminate application | Done
L27.FB | Login | G: 1st line: Builder needs to be all cap: BUILDER Data Collecto | Done | 2019-03-30
L28.FB | Login | G: Logo edges look bad. In email I have attached 3 alternatives to try. Be sure to maintain aspect ratio. | Addressed | 2019-03-30
L28.FB.1 | Login | rlh - Replaced the existing logo with a new one. New image is *much* nicer. | Done | 2019-03-30
L29.FB | Login | G: • Can we drop all the wasted space on top and bottom, have the soft gray background and (Cardno) dark blue border | Done | 2019-03-30
L30.FB | Login | G: • The icons in front of the three text boxes are too small to look good; Either get them bigger or remove. | Done | 2019-03-30
L31.FB | Login | G: • The text in the text boxes is too small as well as the 'Inspector is required' message, larger font please. | Partially addressed | 2019-03-30
L31.FB.R1 | Login | Increased the text box and combo box font size. However, the validation error string will be a little more difficult. It can be done, just not a trvial change. Will do this later. |  | 2019-03-30
L32.FB | Login | G: o To note: It is possible that the BRED file to use line can get long; That text box should be auto wrap and expand to two lines of height as needed | Addressed | 2019-03-30
L32.FB.R1 | Login | Changed the TextBox from to allow wrapping. When a wrap occurs then the box gets taller to accommodate the text. | Done | 2019-03-30
L33 | Login | Need to get rid of main window flash prior to Login display.
Note on F26: George 'Jos' Durtler: The pulldown list is normally to be used. It will have all intended users listed for this project, and thus be a short list, typically 4 - 20. In the Project Config 'PC' file. The More button will retrieve a longer list of possible users retrieved from the BRED file, justed just in case the user was omitted during project setup.

## QC Inspection
ID | Area | Task | Status | Last Activity | NOTES
| QI | QC Inspection
QI1 | QI | Add QA View and ViewModel classes | Done | 2019-03-31
QI2 | QI | Add buttons | Done | 2019-03-31
QI3 | QI | Add data grid | Done | 2019-03-31
QI3FB1 | QI | DATA cells that are not selected should be 100% white, not a light shade of gray as it diminishes the contrast between selected and listed/
FB2 |  | Can we use a background color other than gray for the column headers: Soft blue?
QI4.FB | QI | Tab label: Change QA-Inspection to QC-Inspection
QI15 | QI | Bug: No toolbar on the View.
QI16 | QI | Filter and column name are on two separate rows. Fix.
QI17 | QI | The displayed columns do not agree with the Wireframe's column names.

## QC Inventory
ID | Area | Task | Status | Last Activity | NOTES
| QV | QC Inventory
QV1 | QV | Add QA Inventory View and ViewModel classes | Done | 2019-03-31
QV1FB1 | QV | Tab label: Change QA-Inventory to QC-Inventory
QV2 | QV | Add buttons | Done | 2019-03-31
QV3 | QV | Add data grid | Done | 2019-03-31
QV3FB1 | QI | DATA cells that are not selected should be 100% white, not a light shade of gray as it diminishes the contrast between selected and listed/
FB2 |  | Can we use a background color other than gray for the column headers: Soft blue?
QV3 | QV | Toolbar button row too tall.
QV4 | QV | Ask G: Filter item is orange on the wireframe, not gray. Is this significant?
QV4FB1 | QV | Should be soft yellow to indicate the filter is changeable, but not through editing here, it is done by using the filters for the columns. This area is a summation of filrters in place.
QV5 | QV | Bug: Filter and column header text in two separate rows. Fix
QV6 | QV | Clicking on column header should sort the rows using that column's filter.
QV7 | QV | Currently active filter should show as green
QV8 | QV | View's width is much larger than other Views. Is this necessary? If not, fix.
QV9 | QV | The 'Inventory Issue' filter works in a similar fashion to a 'like' predicate.
QV10 | QV | The 'Inventory Issue' column is misnamed 'InspectionComment Issue'. Fix.

## Photo Managerment
ID | Area | Task | Status | Last Activity | NOTES
| PM | Photo Managerment
PM1 | PM | Add View and ViewModel class skeletons. | Done | 2019-03-31
PM2 | PM | Add Pending cluster
PM3 | PM | Add Existing cluster
PM4 | PM | Add Details cluster
PM5 | PM | Add Title and Description data collection elements
PM6 | PM | Connect Shell buttons to show the View

## Shell
ID | Area | Task | Status | Last Activity | NOTES
| Shell | The Shell is the main window itself which contains the various tabs, trees and so on.
S1 | Shell | Create ShellView and ShellViewModel | Done
S2 | Shell | Bind Title to VM | Done
S3 | Shell | Title string constructed from Build DC + pathname of a file | Done
S3.Q2 | Shell | Ask G: What data is stored in the BRED file? |  |  | PT Notes
S3.Q3 | Shell | G: What data is stored in the config file?Ask |  |  | PT Notes
S4 | Shell | Add Menu | Done
S5 | Shell | Add Submenus | Done
S5FB1 | Shell | View Assigned Systems should have a checkmark in front. If the user clicks the View All Systems, then the checkmark should move here. They are an mutually-exclusive pair. PT: Remembered for duration of session only.
S5FB2 | Shell | Reports ¦ InspectionComment Summary > Inspection Summary
S6 | Shell | Add Toolbar | Done
S7 | Shell | Add buttons to Toolbar | Done
S8 | Shell | Add TreeView | Done
S9 | Shell | Bind TreeView source to ShellViewModel | Done
S10 | Shell | Details TreeView to all expanded | Done
S10.Q1 | Shell | Ask G: Need better definition of tree items / filters. | Done
| Shell | GD: Filtering will exist, but is outside of Mockup scope (because it requires reading project configuration data) Treeview nodes display depends on the mode the user is in: Inventory (tree) Mode (default) or Inspection (tree) Mode (these are the two left-most icons on toolbar) For details see spreadsheet BDC Treeview details_S10.Q1.xlsx
S11 | Shell | Bind selected TreeView item to VM | Done
S12 | Shell | Add grid splitter | Done
S13 | Shell | Add TabView | Done
S14 | Shell | Add Status Bar | Done
S15 | Shell | Add Status Bar contents and bind to ShellViewModel | Done
S17.FB | Shell | Misunderstanding. Those are sub menu items, not another toolbar. Remove from Shell. | Done | 2019-03-30
S17.FB.1 | Shell | Removed the spurious Toolbar and updated the remaining one. | Done | 2019-03-30
S18.FB | Shell | Make title bar font bigger by approx 20% | Pending | 2019-03-30
S18.FB.1 | Shell | This is possible but not trivial. Will delay implementation until after more functional things have been completed. | In process
S18.FB.2 | Shell | G: Let's move the BRED file name to the Status bar on the bottom instead. Make status bar two rows? Increase the font size of the status bar for both rows.
S19.FB | Shell | Make menu text bigger | Done | 2019-03-30
S20.FB | Shell | Make toolbar taller with more space between menu and below. | Done | 2019-03-30
S21.FB | Shell | Build (aka Inventory) and Inspection icons should both be present with some means of indicating what mode currently in, Inventory or Inspect. | Pending
S21.FB.1 | Shell | Added the toolbar buttons but 'currently selected' indication is not yet implemented | In process | 2019-03-30
S22.FB | Shell | Add system and Delete system icons. As we need to distinguish adding system from adding component from adding Section, I have created three simplistic placeholder PNG files to use as toolbar images. Same thing for delete.
S22.FB.1 | Shell | Ask G: The 'add system and delete system icon' thing is a little confusing. Can you elaborate on that? | In process | 2019-03-30 | PT Notes
S22.FB.2 | Shell | G: Clicking the Sys+ button is to bring up what yo see on the Sys+ tab in the wireframe. For Sys-, simpley create function place holder and display placeholder dialog: "Do you want to delete the currently selected System for Facility ####?"
S23 | Shell | Modify the Tab item style to be fat finger compatible and more colorful on selection.
S23.1 | Shell | Add space between Tabs | Done | 2019-04-04
S23.2 | Shell | Make selected tab colorful
S23.2.1 | Shell | Not happy with color. Needs more work | In process | 2019-04-04 | Good Enough!
S24 | Shell | Remember and reassert window placement between sessions | Done | 2019-03-31
S25 | Shell | Bug: Before Login shows, the Shell briefly flashes. It should not. | Done | 2019-03-31
S26 | Shell | Wireframe shows tabs as a series of different blue shades. | In process | 2019-04-04 | Good Enough!
Note on F6: George 'Jos' Durtler: PT: BRED file: Actual data being collected/edited by the inspector. Data describes facilities, inventory, inspections. (Excl. photos)
Note on F7: George 'Jos' Durtler: PT: Project Config file, an MDB file as well, contains project-specific information and is shared by all inspectors on a project. Examples: Photo nmainig convention, photo resolution required, who are the users on the project, what their assignments are.
Note on F34: George 'Jos' Durtler: PT: In our parlance, a System is a high-level classification consisting of a letter and 2 digits. Example: B#0 is a System. All systems that require inspection should be in the starting BRED file, but just in case, Add and delete System functionality will let the user make a change. Example: D30, HVAC was missing in the file and it turns out the facility does have HVAC, so the inspector is to add it.

## Toolbar
ID | Area | Task | Status | Last Activity | NOTES
Toolbar
T1 | Toolbar | Add buttons that show and hide depending upon the currently active tab control | Done | 2019-03-30
T2 | Toolbar | Ask G for an image for Copy Inventory button | Pending | 2019-03-31
T3 | Toolbar | Ask G for an image for Copy Inspection button | Pending | 2019-03-31
T4 | Toolbar | Ask G for an image for Copy Sections button | Pending | 2019-03-31
T5 | Toolbar | Inventory Mode tooltip: "Inventory Mode"
T6 | Toolbar | Inspection Mode tooltip: "Inventory Mode"